## Read me
WorkSwarm usability findings — reviewed and re-categorised
Source | allfindings.xlsx — 108 findings across 3 sheets, 9 personas, 41 concerns.
Reviewed | 2026-09-10, against openJiuwen-ai/jiuwenswarm @ develop 2026-09-05 (0.2.5.beta1) and agent-core 0.1.17.
What changed | Every finding keeps its original text. Added: a 4-role / 8-theme taxonomy, a verdict, evidence, competitor position, and impact/effort/priority.
Rows added | 7 findings from the WorkBuddy competitive review had no equivalent row in the source sheet and are appended as #109-#115. The Source column marks them; filter it to separate them from the original 108.
Not carried over | W6 (spend/budget) is already the COST group, W8 (English parity) is #39/#61/#62, and W9/W10 are portal and marketing copy rather than product findings - see the WorkBuddy response doc for those.
ADDED ROWS — what they are
#109 (W0) | The rename has broken every public install path. pip install jiuwenswarm resolves to 0.2.3 from July; the portal's workswarm-tui is a 404.
#110 (W1) | A zero-key first run already ships (Opencode Zen free models, on by default) but is undocumented and the README states the opposite.
#111 (W2) | jiuwenbox sandbox is opt-in and setup never asks which folders it may use. Distinct from #25, which is the approval policy.
#112 (W3) | Community skills install with no security audit. Distinct from #94, which is ratings and freshness rather than a security scan.
#113 (W4) | The 26 built-in skills are Huawei engineering tools; roughly four suit the office user the product claims.
#114 (W5) | The catalogue accepts only its own hub although skills are already SKILL.md. Distinct from #42, which is cross-instance sharing.
#115 (W7) | Cluster mode is the README default, so a new user's first task takes the slowest and most expensive path.
METHOD — verdicts
Confirmed | Checked against the tree, or a direct restatement of a defect verified elsewhere in this review. Evidence column names the file where one exists.
Confirmed (duplicate) | Real, but the same defect as another row. See the Dup group column — 10 rows collapse into 6 issues.
Partly true | The problem is real but narrower than written; partial support already exists. Fixing the stated version would over-build.
Overstated | The capability largely exists. The finding would send someone to build something already shipped.
Asserted - not re-verified | Plausible and internally consistent, but not independently checked in this pass. Mostly agent-core SDK documentation claims.
METHOD — competitors
Sources | WorkBuddy: Tencent product pages + third-party reviews (no public source). OpenClaw: docs.openclaw.ai + release notes. Hermes: NousResearch/hermes-agent docs. Treat WorkBuddy detail as approximate.
Behind | One or more competitors ship this and market it. Absence is a comparison loss.
Level | Nobody in the set does this well. Fixing it is quality work, not catch-up.
Uncontested | No competitor has it. Doing it is a differentiator, not table stakes.
METHOD — scoring
Impact 1-5 | 5 = decides an evaluation or blocks adoption. 3 = visible friction. 1 = polish.
Effort S/M/L | S = under a day. M = days. L = a sprint or more.
Priority | P0 ship now · P1 next minor · P2 backlog · P3 nice to have. Set from impact x effort, then adjusted for competitive posture.
WHY THE PERSONAS WERE REPLACED
The problem | Four of the nine personas — Shared, Web User, Web Chat, Web Code — are UI surfaces, not people. Self-hoster, Bot-hoster and Web User are the same person on different days. 41 concerns is more categories than a team can hold.
The fix | Two axes instead of one. ROLE answers who is blocked; THEME answers what kind of work fixes it. A finding has exactly one of each.
ROLES (4)
Operator | Installs it, configures it, runs it, keeps it alive. Was: Self-hoster, Bot-hoster.
End user | Does actual work inside the product. Was: Web User, Web Chat, Web Code, most of Shared.
Extender | Adds capability inside it — rails, skills, channels, plugins. Was: Engine Contributor, Skill Author.
Integrator | Builds a separate application on top of it, over the API. Was: Product Builder.
THEMES (8)
1 Get it running | Install, config, credentials, first run, ports, upgrade, diagnostics.
2 Trust & control | Permissions, sandbox, approvals, undo, identity, privacy, blast radius.
3 See what happened | Trajectory, replay, reasoning, progress, token and cost visibility.
4 Do the work | Conversation quality, retry and feedback, search, notifications, artifacts, sharing.
5 Find your way | Naming, information architecture, onboarding, discovery, contextual help.
6 Reach & inclusion | Translation, accessibility, mobile, keyboard.
7 Extend it | Rail and tool APIs, skill authoring and testing, marketplace quality, packaging.
8 Build on it | REST, SDK, protocol schema, webhooks, dev tooling, migration.

## Findings
ID | Role | Theme | Source | Finding | Verdict | Evidence / note | Dup group | Impact | Effort | Priority | Posture | WorkBuddy | OpenClaw | Hermes | Orig sheet | Orig persona | Orig concern
1 | Extender | 7 Extend it | Original sheet | No stable public API or semantic-versioning contract | Asserted - not re-verified | agent-core imported from git SHA; both pkgs 0.x |  | 4 | M | P1 | Behind | Closed source | Documents plugin API + versioned docs | Documents plugin API + versioned docs | Contributors | Engine Contributor | Extension Documentation & Stability
2 | Extender | 7 Extend it | Original sheet | The examples directory is undiscoverable and inconsistent | Partly true | examples/ does exist (examples/harness/*); issue is index+consistency, not absence |  | 3 | M | P2 | Behind | Closed | Plugin examples in docs | Skill/plugin examples | Contributors | Engine Contributor | Extension Documentation & Stability
3 | Extender | 7 Extend it | Original sheet | Adding prompt content from a rail is an undocumented hidden API | Asserted - not re-verified | system_prompt_builder.add_section priority model undocumented |  | 4 | S | P1 | Behind | Closed | Hooks doc names each event | pre_llm_call documented w/ ctx.register_hook() | Contributors | Engine Contributor | Rails & Context API
4 | Extender | 7 Extend it | Original sheet | Rail hook execution order can only be learned from source | Asserted - not re-verified | rail hook order + priority semantics only in source |  | 4 | S | P1 | Behind | Closed | Event hooks doc lists firing order | Hook order documented | Contributors | Engine Contributor | Rails & Context API
5 | Extender | 7 Extend it | Original sheet | The hook context object is undocumented and untyped | Asserted - not re-verified | AgentCallbackContext fields/mutability undocumented |  | 3 | M | P2 | Behind | Closed | ctx documented | ctx documented | Contributors | Engine Contributor | Rails & Context API
6 | Extender | 7 Extend it | Original sheet | The rail extension API has no public documentation | Confirmed | AgentRail 10 hooks + DeepAgentRail +2, no public reference page; only Chinese docs |  | 5 | M | P0 | Behind | Closed | Public plugin/hooks reference | Public plugin/hooks reference | Contributors | Engine Contributor | Rails & Context API
7 | Extender | 7 Extend it | Original sheet | The structured error API isn't documented for rail authors | Asserted - not re-verified | raise_error framework undiscoverable; plain exceptions lose recoverable/fatal/code |  | 3 | S | P2 | Level | Closed | — | — | Contributors | Engine Contributor | Rails & Context API
8 | Extender | 7 Extend it | Original sheet | No CLI to scaffold a new rail or skill | Confirmed | no scaffold CLI in pyproject scripts |  | 3 | M | P2 | Behind | skill-creator (no-code) | Plugin scaffold | hermes skill create | Contributors | Engine Contributor | Extension Testing & Tooling
9 | Extender | 7 Extend it | Original sheet | No integration test layer between unit tests and a full system | Asserted - not re-verified | only mocked unit tests + full e2e |  | 3 | L | P3 | Level | — | — | — | Contributors | Engine Contributor | Extension Testing & Tooling
10 | Extender | 7 Extend it | Original sheet | Writing a rail test requires reverse-engineering mock infrastructure | Asserted - not re-verified | MockLLMModel + _make_agent private/undocumented |  | 2 | S | P2 | Level | — | — | — | Contributors | Engine Contributor | Extension Testing & Tooling
11 | Extender | 7 Extend it | Original sheet | Registering tools from a rail has no developer guide | Asserted - not re-verified | ability_manager.add(ToolCard) only visible in a test file |  | 4 | S | P1 | Behind | Closed | Tool registration documented | 40+ tools, toolset docs | Contributors | Engine Contributor | Tools & Agent Factory
12 | Extender | 7 Extend it | Original sheet | The agent factory has too many undocumented parameters | Confirmed | create_deep_agent has 15+ params (factory.py:455); no param docs |  | 4 | S | P1 | Behind | Closed | — | — | Contributors | Engine Contributor | Tools & Agent Factory
13 | Extender | 7 Extend it | Original sheet | Writing a custom channel has no developer guide | Confirmed | BaseChannel + 11 reference channels, no CHANNELS.md |  | 3 | M | P2 | Behind | Closed | Channel/gateway docs | 17 adapters documented | Contributors | Engine Contributor | Custom Channels
14 | Extender | 7 Extend it | Original sheet | User docs are written like internal design notes | Confirmed | VERIFIED: Modes.md carries deprecate_mode/plan_entry_source + contradicts itself |  | 4 | M | P1 | Behind | Closed | Clean user/dev doc split | Clean user/dev doc split | Contributors | Engine Contributor | Documentation & Stability
15 | Extender | 7 Extend it | Original sheet | Docs are invisible to agents evaluating us (no llms.txt) | Confirmed | VERIFIED: no llms.txt in either repo |  | 4 | S | P1 | Behind | Closed | — | Ships llms.txt + llms-full.txt (PR #18276) | Contributors | Engine Contributor | Documentation & Stability
16 | Operator | 2 Trust & control | Original sheet | Data is kept indefinitely with no expiry controls | Confirmed | only trajectory_ui.retention_days exists; no conversation/memory expiry |  | 3 | M | P2 | Behind | Cloud retention policy | SQLite sessions + archiving | — | Users | Self-hoster | Data Retention
17 | End user | 3 See what happened | Original sheet | No hints about what is consuming the context | Confirmed | no breakdown of what fills the window | COST | 3 | M | P2 | Behind | — | Context/overhead work in 2026.9.1 | — | Users | Self-hoster | Cost & Token Economics
18 | End user | 3 See what happened | Original sheet | No visibility into token usage or session cost | Partly true | OVERSTATED: trajectory token-cost timeline exists; missing piece is budget+alerting | COST | 4 | M | P1 | Behind | Credits + 80%/90% alerts | Per-session cost | Cost-safe loops + session budget | Users | Self-hoster | Cost & Token Economics
19 | Operator | 3 See what happened | Original sheet | Trivial prompts still build the full context | Asserted - not re-verified | full context assembled regardless of prompt size |  | 3 | L | P2 | Level | — | Lower overhead for long conversations | — | Users | Self-hoster | Cost & Token Economics
20 | Operator | 5 Find your way | Original sheet | Documentation is scattered with no guide for common tasks | Confirmed | docs split across YAML comments, /docs, SKILL.md; no task-oriented guide |  | 3 | M | P2 | Behind | — | Task-oriented docs site | Task-oriented docs site | Users | Self-hoster | Running & Managing the Instance
21 | Operator | 6 Reach & inclusion | Original sheet | Logs and config mix languages unpredictably | Confirmed | VERIFIED: config.yaml comments alternate zh/en mid-section |  | 3 | M | P2 | Behind | — | — | — | Users | Self-hoster | Running & Managing the Instance
22 | Operator | 1 Get it running | Original sheet | No visibility into which ports and URLs are in use | Confirmed | no port/URL echo after start; silent port fallback |  | 4 | S | P1 | Behind | — | Prints gateway URL + health | Prints REPL/gateway target | Users | Self-hoster | Running & Managing the Instance
23 | Operator | 2 Trust & control | Original sheet | Permission rules can only be edited in raw YAML | Confirmed | tiered policy is regex YAML only; dialog shows generic 'full access' |  | 4 | M | P1 | Behind | — | Permission scoping in Control UI | — | Users | Self-hoster | Running & Managing the Instance
24 | Operator | 1 Get it running | Original sheet | Upgrading can silently break an existing config | Partly true | OVERSTATED: config_version (config.yaml:3) and migrate_config_from_template() both exist; what's missing is a breaking-change changelog |  | 3 | S | P2 | Level | — | Migration on 2.0 upgrade | — | Users | Self-hoster | Running & Managing the Instance
25 | Operator | 2 Trust & control | Original sheet | Default permissions are off, contradicting the README | Confirmed | VERIFIED: permissions.enabled:false in all 3 templates; README:158 says the opposite |  | 5 | S | P0 | Behind | Sandbox+approval on by default | Ask-first chosen at onboarding | Approval engine on | Users | Self-hoster | Running & Managing the Instance
26 | Operator | 2 Trust & control | Original sheet | Granted permissions are invisible once granted | Confirmed | approval_overrides has no in-UI ledger |  | 3 | M | P2 | Behind | — | Permission scoping visible | — | Users | Self-hoster | Running & Managing the Instance
27 | Operator | 1 Get it running | Original sheet | Missing optional extras fail when used, not at startup | Confirmed | VERIFIED: no extras check in start_services.py |  | 3 | S | P2 | Level | — | Health check at onboarding | Single binary - N/A | Users | Self-hoster | Startup & Configuration
28 | Operator | 1 Get it running | Original sheet | Setup ends before credentials are tested | Confirmed | ModelSetupGuide tour ends at the models panel | SETUP | 5 | M | P0 | Behind | Bundled model, nothing to test | Blocks until a live completion succeeds | hermes setup validates | Users | Self-hoster | Startup & Configuration
29 | Operator | 1 Get it running | Original sheet | The config file has no validation or check tool | Confirmed | one file: models+memory+channels+permissions+observability+SSH; undocumented ${VAR:-default} |  | 4 | M | P1 | Behind | — | Config written by onboarding | YAML+env merge, wizard-driven | Users | Self-hoster | Startup & Configuration
30 | Operator | 1 Get it running | Original sheet | Wrong credentials surface only on the first chat, never at startup | Confirmed (duplicate) | same defect as #28 | SETUP | 5 | M | P0 | Behind | Bundled model | Live completion gate | Wizard validates | Users | Self-hoster | Startup & Configuration
31 | Operator | 1 Get it running | Original sheet | Headless installs silently become Chinese installs | Confirmed | VERIFIED: common/utils.py:536-538 returns 'zh' when stdin is not a TTY |  | 5 | S | P0 | Behind | — | --non-interactive with explicit flags | Install script is locale-neutral | Users | Self-hoster | Startup & Configuration
32 | Operator | 1 Get it running | Original sheet | Nothing verifies the model before the first conversation | Confirmed (duplicate) | same defect as #28 | SETUP | 5 | M | P0 | Behind | Bundled model | Live completion gate | Wizard validates | Users | Self-hoster | Startup & Configuration
33 | Operator | 1 Get it running | Original sheet | No minimal starting point for config (818 keys) | Confirmed | VERIFIED: 1,510 lines / 818 keys / depth 8 |  | 4 | M | P1 | Behind | — | Config is not the interface | Wizard + REPL cover common path | Users | Self-hoster | Startup & Configuration
34 | Operator | 1 Get it running | Original sheet | Running the CLI without config gives no next step | Confirmed | bare CLI with no config gives unclear error; --help has no first-run path |  | 3 | S | P2 | Behind | — | onboard is the entry point | hermes drops into guided REPL | Users | Self-hoster | First Run
35 | Operator | 1 Get it running | Original sheet | Setup wizard ends before the model is confirmed working | Confirmed (duplicate) | same defect as #28 | SETUP | 5 | M | P0 | Behind | Bundled model | Live completion gate | Wizard validates | Users | Self-hoster | First Run
36 | Operator | 1 Get it running | Original sheet | You aren't told when a subsystem fails | Confirmed | non-critical subsystem failures are silent (memory provider, OTel, channel init) |  | 4 | M | P1 | Behind | — | Host status dashboard CPU/mem/disk/uptime | — | Users | Self-hoster | Health & Degradation
37 | End user | 3 See what happened | Original sheet | No per-model budget dashboard | Confirmed (duplicate) | same need as #18 - budget layer on existing cost data | COST | 4 | L | P2 | Behind | Credits + 80%/90% alerts | Per-session cost | Session budget | Users | Self-hoster | Cost & Tokens
38 | Operator | 1 Get it running | Original sheet | No diagnostic ('doctor') command | Confirmed | VERIFIED: no doctor/diagnose entry point in pyproject scripts | DOCTOR | 4 | M | P1 | Behind | — | Gateway health check + status dashboard | Single binary removes most failure modes | Users | Self-hoster | Diagnostics
39 | Operator | 6 Reach & inclusion | Original sheet | English docs show the Chinese UI | Confirmed | VERIFIED: 55 of 144 image refs in docs/en use CJK-named screenshots |  | 3 | M | P2 | Behind | — | 20+ locales, localized docs | — | Users | Self-hoster | Documentation
40 | Operator | 2 Trust & control | Original sheet | No login on the Web UI: local Web users share one identity | Confirmed | VERIFIED: no web auth; only OpenAI account-login helpers in the handler |  | 5 | L | P1 | Behind | — | User auth + permission scoping + device pairing | Gateway auth | Users | Bot-hoster | Identity & Isolation
41 | Operator | 2 Trust & control | Original sheet | No multi-tenancy: every user shares one workspace | Confirmed | single-workspace; user_id is routing/logging only |  | 5 | L | P1 | Behind | — | Roles + shared cloud sessions | Per-platform identity | Users | Bot-hoster | Identity & Isolation
42 | Extender | 7 Extend it | Original sheet | No shared skill library across instances | Confirmed | skills are per-workspace; no cross-instance sharing |  | 3 | M | P2 | Behind | SkillHub + ClawHub | Plugin/skill marketplace | agentskills.io standard | Users | Bot-hoster | Shared Skill Library
43 | End user | 4 Do the work | Original sheet | Error messages give no explanation or next step | Confirmed | bare error strings reached production (cli/render.py:200) |  | 4 | M | P1 | Level | — | Errors explain + recovery options | — | Users | Shared | Errors & Feedback
44 | End user | 4 Do the work | Original sheet | No way to rate, retry or correct an agent answer | Confirmed | VERIFIED: no thumbs/regenerate on assistant messages - only on ProactiveRecommendationCard |  | 5 | M | P0 | Behind | — | Retry/regenerate standard | Retry/regenerate standard | Users | Shared | Errors & Feedback
45 | End user | 4 Do the work | Original sheet | Errors don't point to the log entry with more detail | Confirmed | errors don't reference the log entry |  | 3 | S | P2 | Level | — | Logs + diagnostics in Control UI | — | Users | Shared | Errors & Feedback
46 | End user | 4 Do the work | Original sheet | Rate limits and API failures hang or show nothing useful | Confirmed | 429/503 shows generic error or silent hang; no backoff indicator |  | 4 | M | P1 | Behind | — | Reliability/recovery pass in 2026.9.2 | Cost-safe loop w/ retry | Users | Shared | Errors & Feedback
47 | End user | 4 Do the work | Original sheet | Clarification questions appear with no context | Confirmed | clarification arrives without the stuck-state context |  | 2 | S | P3 | Level | — | — | — | Users | Shared | Conversation
48 | End user | 4 Do the work | Original sheet | Long agent replies have no structure aids | Confirmed | no ToC / jump / folding on long replies |  | 2 | M | P3 | Level | — | Mermaid + rich chat surfaces | — | Users | Shared | Conversation
49 | End user | 4 Do the work | Original sheet | No immediate feedback between submit and the first chat event | Partly true | gap is only the pre-first-event window; live progress does exist afterwards |  | 2 | S | P3 | Level | — | — | — | Users | Shared | Conversation
50 | End user | 4 Do the work | Original sheet | No advance warning before context compression | Partly true | ContextCompressionLines already shows it during/after; only advance warning is missing |  | 2 | S | P3 | Level | — | — | — | Users | Shared | Conversation
51 | End user | 4 Do the work | Original sheet | Past conversations can't be searched | Confirmed | VERIFIED: no search in SessionSidebar |  | 4 | S | P1 | Behind | — | Session groups, filtering, archiving | — | Users | Shared | History & Notifications
52 | End user | 4 Do the work | Original sheet | No notification when a long task finishes | Confirmed | no desktop notification/sound/badge on completion | NOTIFY | 4 | M | P1 | Behind | — | Background sessions + desktop companion | Gateway pushes to chat apps | Users | Shared | History & Notifications
53 | End user | 4 Do the work | Original sheet | Background tasks look identical to idle sessions | Confirmed | background sessions show no activity indicator in the sidebar |  | 3 | S | P2 | Behind | — | Running-session indicators | — | Users | Shared | History & Notifications
54 | End user | 2 Trust & control | Original sheet | Users aren't told what the agent is allowed to do before it acts | Confirmed | no pre-session summary of what the agent may do |  | 4 | M | P1 | Behind | — | Full-access vs ask-first shown at onboarding | — | Users | Shared | Control & Continuity
55 | End user | 2 Trust & control | Original sheet | Unclear what the agent does when a session disconnects | Confirmed | disconnect behaviour undocumented and invisible; no reconnect flow |  | 4 | M | P1 | Behind | — | Background sessions - explicitly solved | — | Users | Shared | Control & Continuity
56 | End user | 2 Trust & control | Original sheet | A crash loses in-progress tasks with no way to resume | Confirmed | no checkpointing; crash loses in-progress work |  | 5 | L | P1 | Behind | — | SQLite sessions + recovery improvements | — | Users | Shared | Control & Continuity
57 | End user | 2 Trust & control | Original sheet | Users can't see what the agent has remembered | Partly true | PARTLY: a workspace/memory viewer string exists ('View agent workspace files and memory content'); browse/search/edit/delete is the gap |  | 4 | M | P1 | Behind | — | Memory import + management | 8 memory backends | Users | Shared | Memory & Privacy
58 | End user | 2 Trust & control | Original sheet | No way to see what personal data is sent to the model | Confirmed | assembled prompt is not inspectable |  | 4 | M | P1 | Uncontested | — | — | — | Users | Shared | Memory & Privacy
59 | Operator | 1 Get it running | Original sheet | No single command to gather diagnostics for a bug report | Confirmed (duplicate) | same need as #38 | DOCTOR | 4 | M | P1 | Behind | — | Diagnostics in Control UI | — | Users | Shared | Help & Diagnostics
60 | End user | 5 Find your way | Original sheet | No help or tooltips at the point of confusion | Confirmed | no field tooltips or contextual '?' links |  | 2 | M | P3 | Level | — | — | — | Users | Shared | Help & Diagnostics
61 | End user | 6 Reach & inclusion | Original sheet | GUI text is not fully translated | Confirmed (duplicate) | same defect as #62 | I18N | 4 | M | P1 | Behind | — | 20+ locales | — | Users | Web User | Language
62 | End user | 6 Reach & inclusion | Original sheet | The newest features are the least translated | Confirmed | VERIFIED: 366 CJK literals in 74 files outside locale bundles | I18N | 4 | M | P1 | Behind | — | 20+ locales, synced prefs | — | Users | Web User | Language
63 | End user | 5 Find your way | Original sheet | Settings are organized by code module, not by user task | Confirmed | settings modules mirror the codebase, not user goals |  | 3 | M | P2 | Behind | — | Task-oriented settings | — | Users | Web User | Navigation & Settings
64 | End user | 5 Find your way | Original sheet | Skills and connectors are split apart though they're the same kind of thing | Confirmed | Skills and Connector Market are separate top-level items |  | 2 | S | P3 | Level | — | Plugins+skills unified | — | Users | Web User | Navigation & Settings
65 | End user | 5 Find your way | Original sheet | The activity view is hidden behind an unclear name | Confirmed | nav item labelled 'TraceHound' - hides the one capability no competitor has |  | 4 | S | P0 | Behind | — | Activity view is prominent | — | Users | Web User | Navigation & Settings
66 | End user | 5 Find your way | Original sheet | Empty screen offers no example or next step | Confirmed | empty conversation shows a blank input; WelcomeBubble not discoverable |  | 3 | S | P1 | Behind | — | Home surface with starting points | — | Users | Web User | Discovery & Onboarding
67 | End user | 5 Find your way | Original sheet | No guidance introduces features after first run | Confirmed | no post-setup feature introduction |  | 3 | M | P2 | Behind | — | Onboarding continues into the app | — | Users | Web User | Discovery & Onboarding
68 | End user | 5 Find your way | Original sheet | Powerful features exist but are never surfaced | Confirmed | trajectory, OTel, debug traces, coding memory, SSH all off with no hint |  | 4 | M | P1 | Behind | — | Features surfaced in Control UI | — | Users | Web User | Discovery & Onboarding
69 | End user | 5 Find your way | Original sheet | Agent modes have no user-facing names or descriptions | Confirmed | VERIFIED: modes named from implementation; no tooltip or one-liner |  | 4 | S | P1 | Behind | — | Plain-language agent config | — | Users | Web User | Discovery & Onboarding
70 | End user | 6 Reach & inclusion | Original sheet | No high-contrast or large-text option | Confirmed | no high-contrast theme, no font-size control |  | 2 | M | P3 | Behind | — | Themes + typography options | — | Users | Web User | Accessibility
71 | End user | 6 Reach & inclusion | Original sheet | No screen-reader support; streaming output isn't announced | Overstated | OVERSTATED: 262 aria-label uses and aria-live present in ChatPanel/InputArea/subagent. Real issue is coverage+audit, not absence |  | 3 | M | P2 | Uncontested | — | — | — | Users | Web User | Accessibility
72 | End user | 6 Reach & inclusion | Original sheet | The web UI isn't usable as a proper mobile experience | Confirmed | 3-panel layout collapses poorly at 375px |  | 3 | L | P2 | Behind | — | Fuller Android experience (2026.9.1) | — | Users | Web User | Mobile
73 | End user | 6 Reach & inclusion | Original sheet | No installable or offline (PWA) version | Confirmed | VERIFIED: no manifest.json, no service worker |  | 2 | M | P3 | Behind | — | Mobile + device pairing | — | Users | Web User | Mobile
74 | End user | 3 See what happened | Original sheet | No way to see every LLM/tool call and token behind a run | Partly true | trajectory + token-cost timeline already exist; the gap is an interactive span waterfall | REPLAY | 3 | L | P2 | Level | — | Activity stream (no waterfall) | — | Users | Web User | Explanation & Visibility
75 | End user | 3 See what happened | Original sheet | No live picture of how the swarm is coordinating | Confirmed | team state is flat lists; no live coordination graph |  | 3 | L | P2 | Uncontested | — | — | — | Users | Web User | Explanation & Visibility
76 | End user | 3 See what happened | Original sheet | Can't scrub back through what the agent did, turn by turn | Overstated | OVERSTATED: trajectory archive + replay shipped 2026-08-21; per-member lanes and token timeline exist | REPLAY | 3 | M | P2 | Uncontested | — | — | — | Users | Web User | Explanation & Visibility
77 | End user | 4 Do the work | Original sheet | Can't compare versions of a generated artifact | Confirmed | artifacts render one at a time; no gallery or version diff |  | 2 | M | P3 | Uncontested | — | — | — | Users | Web User | Safety & Undo
78 | End user | 3 See what happened | Original sheet | The task list doesn't show progress moving | Confirmed | goals/todos are flat rows; no board view |  | 2 | M | P3 | Level | — | Task workspaces (2026.9.2) | — | Users | Web User | Control & Continuity
79 | End user | 4 Do the work | Original sheet | The agent's output only lands as one final message | Confirmed | no live canvas re-rendering as the agent works |  | 3 | L | P2 | Behind | — | Home/work surfaces | — | Users | Web User | Conversation
80 | End user | 4 Do the work | Original sheet | No way to know the agent's state without opening the window | Confirmed (duplicate) | desktop half of #52 | NOTIFY | 4 | M | P1 | Behind | — | Desktop companion + native toasts | — | Users | Web User | History & Notifications
81 | End user | 4 Do the work | Original sheet | No control over reply length or writing style | Confirmed | no global or per-message length/style control |  | 3 | S | P1 | Behind | — | Style/persona config | Persona + style config | Users | Web Chat | Reply
82 | End user | 4 Do the work | Original sheet | Conversations can only be shared as a flat image | Confirmed | shareImageExport PNG is the only share path |  | 3 | M | P2 | Behind | — | Share links + shared sessions | — | Users | Web Chat | Sharing
83 | End user | 3 See what happened | Original sheet | Agent reasoning is hidden in a separate panel | Confirmed (duplicate) | discoverability half of #65/#76 - reasoning exists, it's in a panel you must know to open | REPLAY | 3 | M | P2 | Behind | — | Side chat about a run | — | Users | Web Code | Explanation
84 | End user | 3 See what happened | Original sheet | Tool calls show what ran but not why | Confirmed | ToolCallDisplay shows name/args/result but never the reason for the choice |  | 3 | M | P2 | Behind | — | Preamble headlines explain intent | — | Users | Web Code | Explanation
85 | End user | 2 Trust & control | Original sheet | File changes are applied with no preview or approval | Partly true | CodeChangesCard exists; unclear whether it previews before or summarizes after - needs a UX decision, not a build |  | 4 | M | P1 | Behind | — | Diff preview | Diff preview | Users | Web Code | Safety & Undo
86 | End user | 2 Trust & control | Original sheet | Destructive external actions fire without confirmation | Confirmed | no per-call confirmation for sends/webhooks; permissions can only block a tool entirely |  | 5 | M | P0 | Behind | — | Approval gates on sensitive actions | Approval engine | Users | Web Code | Safety & Undo
87 | End user | 2 Trust & control | Original sheet | Sent messages and API calls can't be undone | Confirmed | external sends are irreversible with no UI record |  | 3 | L | P2 | Uncontested | — | — | — | Users | Web Code | Safety & Undo
88 | End user | 3 See what happened | Original sheet | No step-wise progress or ETA while a skill runs | Partly true | turn-level spinner+timer exist; skill-level step/ETA is the gap |  | 2 | M | P3 | Level | — | Progress indicators | — | Users | Web Code | Progress
89 | End user | 6 Reach & inclusion | Original sheet | The UI can't be driven fully by keyboard | Partly true | PARTLY: 48 onKeyDown handlers exist; claim is unverified coverage, not absence |  | 2 | M | P2 | Uncontested | — | — | — | Users | Web Code | Keyboard
90 | End user | 6 Reach & inclusion | Original sheet | Core actions have no keyboard shortcuts | Confirmed | only Enter submits; no documented shortcuts |  | 2 | S | P2 | Behind | — | Keyboard shortcuts in Control UI | — | Users | Web Code | Keyboard
91 | Extender | 7 Extend it | Original sheet | Creating a skill has no clear entry point | Confirmed | routing between 3 creator skills is hidden inside a SKILL.md; no UI entry |  | 4 | M | P1 | Behind | — | skill-creator + 1-click SkillHub install | hermes skill create | Builders | Skill Author | Authoring & Testing
92 | Extender | 7 Extend it | Original sheet | Skill Python dependencies and conflicts are invisible | Confirmed | requirements.txt installed at load with no dependency UI |  | 3 | M | P2 | Uncontested | — | — | — | Builders | Skill Author | Authoring & Testing
93 | Extender | 7 Extend it | Original sheet | Skills can only be tested through a live chat | Confirmed | no sample-input test harness in the UI |  | 4 | L | P1 | Uncontested | — | — | — | Builders | Skill Author | Authoring & Testing
94 | Extender | 7 Extend it | Original sheet | Marketplace shows no ratings, usage or freshness | Confirmed | VERIFIED: no rating/downloads/freshness in MarketplacePage.tsx |  | 4 | M | P0 | Behind | — | SkillHub/ClawHub rank by downloads, ratings, freshness; skill-vetter risk grades | agentskills.io standard | Builders | Skill Author | Marketplace
95 | Extender | 7 Extend it | Original sheet | Skill updates can't be reviewed or rolled back | Confirmed | skill updates overwrite; no version history or rollback |  | 3 | M | P2 | Behind | — | Versioned skill packages | — | Builders | Skill Author | Packaging & Distribution
96 | Integrator | 2 Trust & control | Original sheet | No API authentication: fine locally, a real risk once exposed | Confirmed | VERIFIED: E2AAuth is carried in the model but never validated |  | 5 | L | P1 | Behind | — | Auth + token/password modes | Gateway auth | Builders | Product Builder | Connection & Security
97 | Integrator | 2 Trust & control | Original sheet | WebSocket origin checks are off by default and undocumented | Confirmed | VERIFIED: ws_origin.is_origin_check_enabled() requires env=='1' - off by default, undocumented |  | 4 | S | P0 | Behind | — | One trust boundary per gateway | — | Builders | Product Builder | Connection & Security
98 | Integrator | 2 Trust & control | Original sheet | No single answer to what a gateway can reach | Confirmed | authority spread over 6 mechanisms + per-channel differences |  | 4 | M | P1 | Behind | — | One trust boundary per gateway (2.0 headline) | — | Builders | Product Builder | Connection & Security
99 | Integrator | 8 Build on it | Original sheet | External apps can only reach the agent over WebSocket, with no REST | Partly true | NUANCE: FastAPI is already mounted (container_file_http.py) for file routes - so no agent-level REST, but the stack is there and the fix is cheaper than stated |  | 5 | M | P0 | Behind | — | Gateway HTTP + WS | REST API + WebSocket + MCP/ACP | Builders | Product Builder | Transport & Protocol
100 | Integrator | 8 Build on it | Original sheet | The E2A protocol spec is prose, not a machine-readable schema | Confirmed | E2A spec is 2 Markdown files; no JSON Schema/AsyncAPI/type stubs |  | 4 | M | P1 | Behind | — | Documented API | — | Builders | Product Builder | Transport & Protocol
101 | Integrator | 8 Build on it | Original sheet | No published client SDK, so every app re-implements the protocol | Confirmed | WebSocketAgentServerClient is internal/unpublished; no JS/TS client |  | 5 | L | P1 | Behind | — | Client libraries | Published SDK + 17 adapters | Builders | Product Builder | Transport & Protocol
102 | Integrator | 8 Build on it | Original sheet | Session API methods have no documented response shapes | Confirmed | ~30 session methods with no documented request/response shapes |  | 4 | M | P1 | Behind | — | Documented session API | — | Builders | Product Builder | Transport & Protocol
103 | Integrator | 8 Build on it | Original sheet | Only shell-command hooks exist; there's no real webhook delivery | Confirmed | VERIFIED: hooks are type:command/shell only - no HTTP type, retry, HMAC or delivery guarantee |  | 4 | M | P1 | Behind | — | Webhooks + integrations | Webhook delivery | Builders | Product Builder | Integration & Tooling
104 | Integrator | 8 Build on it | Original sheet | No local stub or dev mode for testing integrations | Confirmed | no stub/echo/playback/Compose for CI |  | 4 | M | P1 | Uncontested | — | — | — | Builders | Product Builder | Integration & Tooling
105 | Integrator | 8 Build on it | Original sheet | No migration/import path from an existing agent setup | Confirmed | CLAUDE.md/AGENTS.md/MCP defs never read at init despite running those runtimes |  | 3 | M | P2 | Behind | — | --flow import from Claude Code, Codex, Hermes | — | Builders | Product Builder | Integration & Tooling
106 | Integrator | 2 Trust & control | Original sheet | Browser runs stop at a blocker with nowhere to go | Confirmed | blockers detected but no human handoff; unattended runs die |  | 3 | M | P2 | Level | — | — | — | Builders | Product Builder | Integration & Tooling
107 | Extender | 7 Extend it | Original sheet | The SDK has no reference cron backend | Confirmed | VERIFIED: harness/tools/cron.py is protocol+factory only. NOTE: the product ships a full scheduler (~4,500 lines) - this is SDK-only |  | 2 | M | P3 | Level | — | Cron in Control UI | Cron scheduling | Builders | Product Builder | Integration & Tooling
108 | Extender | 7 Extend it | Original sheet | Headline capabilities ship undocumented | Confirmed | VERIFIED: no Heartbeat.md / Trajectory.md / Marketplace.md among 53 docs/en files |  | 4 | M | P1 | Behind | — | Documented features | Documented features | Builders | Product Builder | Documentation
109 | Operator | 1 Get it running | Added - WorkBuddy review (W0) | The in-flight rename has broken every public install path | Confirmed | VERIFIED on PyPI: README says `pip install jiuwenswarm` -> resolves to 0.2.3 (2026-07-14) because 0.2.4b3 is a prerelease. Portal says `pip install workswarm-tui` -> 404, does not exist. pyproject.toml already declares name='workswarm'; workswarm 0.2.5 shipped 2026-08-20. Last jiuwenswarm release 2026-08-06 = the day the README's Latest Updates stops. |  | 5 | M | P0 | Behind | One name, one command | One name, one command | One-line installer | (added) | (added) | (not in source sheet)
110 | Operator | 1 Get it running | Added - WorkBuddy review (W1) | A zero-key first run already ships, but is hidden and the README says the opposite | Confirmed | VERIFIED: server/runtime/opencode_zen.py fetches free key-less models at AgentServer start and falls back to deepseek-v4-flash-free; models.enable_free_models ships true; its docstring says the module exists to 'make JiuwenSwarm work out of the box'. Zero mentions in the 53 docs/en files or either portal page - only a settings-toggle tooltip. README:118 says 'A default model is the one piece of configuration you cannot skip.' A recent commit moved free models BELOW paid ones in the picker. Cheapest competitive answer available. |  | 5 | S | P0 | Behind | 5,000 free credits, no API key, working in 2 min | Onboarding gates on a live completion | Wizard validates provider | (added) | (added) | (not in source sheet)
111 | Operator | 2 Trust & control | Added - WorkBuddy review (W2) | The sandbox is built but opt-in, and setup never asks which folders it may use | Confirmed | VERIFIED: jiuwenbox does Landlock confinement with per-path write allow/deny and command exclusion, but it is opt-in via `/sandbox enable` (docs/en/SlashCommands.md:698). Combined with #25 (permissions.enabled:false) a fresh install has neither gate on. Distinct from #25: that row is the approval policy, this is the execution sandbox plus the missing folder-authorization step. Folder-auth friction is WorkBuddy's most-reported complaint - gather grants once at setup, not per action. |  | 5 | M | P0 | Behind | Authorized folders + container isolation, on by default | Ask-first vs full-access chosen at onboarding | Terminal backends incl. Docker/SSH | (added) | (added) | (not in source sheet)
112 | Extender | 7 Extend it | Added - WorkBuddy review (W3) | Community skills install with no security audit | Confirmed | VERIFIED: no risk/audit/scan stage anywhere in server/runtime/skill/skill_manager.py, and skills install via .zip upload. Until #25/#111 land, unvetted skill code runs with permissions disabled. Adjacent to but distinct from #94 (which is ratings/usage/freshness - quality signals, not a security scan). Parts already exist to build it: shell AST parsing in the permission layer, the tiered severity vocabulary, and /security-review. |  | 5 | M | P0 | Behind | skill-vetter audits before activation: network calls, credential theft, file access, obfuscation, root - graded LOW/MEDIUM/HIGH/EXTREME | Plugin install review | agentskills.io standard | (added) | (added) | (not in source sheet)
113 | End user | 5 Find your way | Added - WorkBuddy review (W4) | The built-in skills are Huawei engineering tools, not office work | Confirmed | VERIFIED: 26 built-ins in resources/agent/workspace/skills/ - ascend-moe-optimizer, deepep-to-cam-converter, harmonyos-dev-suite, skvm-jit, gitcode-api and similar. Roughly four an office worker would recognise (advanced-daily-report, ppt-creation, financial-document-parser, openJiuwen-DeepSearch). The first thing a new user opens contradicts the positioning on the front page. Packaging, not engineering. |  | 4 | M | P1 | Behind | 20-30+ office packs (analysis, drafting, reporting), one-click enable | Skills marketplace | 40+ tools, bundled skills | (added) | (added) | (not in source sheet)
114 | Extender | 7 Extend it | Added - WorkBuddy review (W5) | The catalogue accepts only its own hub, though the format is already portable | Confirmed | VERIFIED: skills are stored as SKILL.md (43 in the tree), the same de-facto standard the wider ecosystem uses - so accepting outside skills is a policy decision, not a port. Competing catalogue-against-catalogue with Tencent is the losing move. Distinct from #42, which is sharing skills across two of your own instances. |  | 4 | M | P1 | Behind | Imports OpenClaw-format skills; lists ClawHub beside its own SkillHub | ClawHub is the reference hub | agentskills.io open standard | (added) | (added) | (not in source sheet)
115 | End user | 5 Find your way | Added - WorkBuddy review (W7) | Cluster mode is the default, so the first task is the slowest and most expensive path | Confirmed | VERIFIED: README:140 marks Cluster Mode as the default. A new user's very first request therefore goes through leader decomposition and team assembly - the slowest, priciest and most confusing path, at the exact moment they are deciding whether the product works. Cold-start work and sandbox prewarming are undone by the mode default. Distinct from #69 (mode naming) and #19 (context assembly cost). |  | 4 | S | P0 | Behind | Single fast path by default | Single agent by default | Single agent REPL by default | (added) | (added) | (not in source sheet)

## Roll-up
Findings by role x priority | [5 empty] | Counts cover all 115 rows (108 original + 7 added).
| P0 | P1 | P2 | P3 | Total
Operator | 9 | 9 | 9 | 0 | 27
End user | 4 | 19 | 18 | 11 | 52
Extender | 3 | 11 | 9 | 2 | 25
Integrator | 2 | 7 | 2 | 0 | 11
Total | 18 | 46 | 38 | 13 | 115
Findings by theme x priority
| P0 | P1 | P2 | P3 | Total
1 Get it running | 7 | 6 | 3 | 0 | 16
2 Trust & control | 4 | 11 | 4 | 0 | 19
3 See what happened | 0 | 1 | 8 | 2 | 11
4 Do the work | 1 | 6 | 4 | 5 | 16
5 Find your way | 2 | 4 | 3 | 2 | 11
6 Reach & inclusion | 0 | 2 | 6 | 2 | 10
7 Extend it | 3 | 11 | 9 | 2 | 25
8 Build on it | 1 | 5 | 1 | 0 | 7
Total | 18 | 46 | 38 | 13 | 115
Verdict breakdown
Verdict | Count
Confirmed | 85
Confirmed (duplicate) | 8
Partly true | 11
Overstated | 2
Asserted - not re-verified | 9
Competitive posture
Posture | Count
Behind | 86
Level | 19
Uncontested | 10

## Merge map
Dup group | Merge into | Also covered by | One-line issue
SETUP | #28 | #30, #32, #35 | Setup finishes without ever proving the model works. Four rows, one fix.
COST | #18 | #17, #37 | Cost data already exists in the trajectory timeline; what is missing is a budget, a breakdown and a threshold alert.
DOCTOR | #38 | #59 | One diagnostic command covers both the pass/fail check and the bug-report bundle.
I18N | #62 | #61 | One backlog: move the 366 literals into the locale bundles and add a CI lint.
REPLAY | #76 | #74, #83 | Replay already shipped. The real defects are discoverability (#65) and the missing span waterfall — not the absence of replay.
NOTIFY | #52 | #80 | Web notification and desktop tray/toast are one feature with two surfaces.
Net: 108 original rows -> 98 distinct issues; plus 7 added rows = 105 tracked issues.
Adjacent but NOT duplicates - keep both
Added row | Looks like | Why they are different
#111 | #25 | #25 is the approval policy being off; #111 is the execution sandbox being opt-in and no folder-authorization step at setup.
#112 | #94 | #94 is marketplace quality signals (ratings, downloads, freshness); #112 is a security audit run before a skill is allowed to execute.
#114 | #42 | #42 is sharing skills between two of your own instances; #114 is accepting skills authored for another product.
#115 | #69 | #69 is that mode names are meaningless; #115 is that the default mode is the wrong one for a first task.
#110 | #28 | #28 is that setup never proves the model works; #110 is that a working key-less model already ships and is hidden.